## PeopleSoft CR
Poject Name | Issue Name | MileStone | Status | Description
Server App | PS-New-LeaveSubmitMessage-EmployeeType-Addition | mil-2025-JUN-Retrofit-Of-Fusion-Back-To-PeopleSoft | Live | Merged into milestone , patch is deployed on Prod but milestone is not merged into master
Server App | PS-Leave-Apply-By-RA | mil-2025-JUN-Retrofit-Of-Fusion-Back-To-PeopleSoft | Live | Merged into milestone , patch is deployed on Prod but milestone is not merged into master
Server App | PS-Muster-Apply-By-RA | mil-2025-JUN-Retrofit-Of-Fusion-Back-To-PeopleSoft | Live | Merged into milestone , patch is deployed on Prod but milestone is not merged into master
Server App | PS-Leave-Document-API-Integration | mil-2025-NOV-Leave-Document-API-Integration | UAT | Sick Leave with Document, development done on UAT, testing is ongoing from client side
Server IB | PS-Leave-V1 | mil-2025-JUN-Retrofit-Of-Fusion-Back-To-PeopleSoft | Live | Merged into milestone , patch is deployed on Prod but milestone is not merged into master
Server IB | PS-Leave-Apply-By-RA | mil-2025-JUN-Retrofit-Of-Fusion-Back-To-PeopleSoft | Live | Merged into milestone , patch is deployed on Prod but milestone is not merged into master
Server IB | PS-Muster-Apply-By-RA | mil-2025-JUN-Retrofit-Of-Fusion-Back-To-PeopleSoft | Live | Merged into milestone , patch is deployed on Prod but milestone is not merged into master
Server IB | PS-Switch-To-HttpClient | mil-2025-JUN-Retrofit-Of-Fusion-Back-To-PeopleSoft | UAT | Migrated the old wsimport code to httpclient to resolve the socket exception issue. still on UAT and testing is pending
Server IB | PS-Leave-Document-API-Integration | mil-2025-NOV-Leave-Document-API-Integration | UAT | Sick Leave with Document, development done on UAT, testing is ongoing from client side
Server IB | PS-Sick-Leave_Validation-Format-Change | mil-2025-JUN-Retrofit-Of-Fusion-Back-To-PeopleSoft | UAT | Trimmed the extra xml components coming from peoplesoft in sick leave validation messages, still on uat and in testing phase
DB | PeopleSoft-DB-Patch | mil-2025-JUN-Retrofit-Of-Fusion-Back-To-PeopleSoft | Live | DB patch is deployed in Production

## SignOut CR
Poject Name | Issue Name | MileStone | Status | Description
Server App | Adding-Sign-Out-Feature | mil-2025-NOV-Signout-Feature-Implementation | UAT | Adding Type Parameter for geo attendance for normal employee , default is IN

## ICare Category CR
Poject Name | Issue Name | MileStone | Status | Description
Admin | Icare-Category-List-Manager | mil-2025-NOV-Admin-iCare-Category-Management | UAT | Add, Edit and Delete functionality for ICare Categories with priority management
DB |  |  | UAT | Shared with sakshi, not uploaded on gitlab as it is still beign developed

## CORP Attire Issue
Projects | Tables | Procedures | Functions | Survey Ids
Admin | MSTR_SURVEY_QSTN_TBL | GET_SURVEY_QUESTIONS | showCorporateSurvey | Male: 576 Female: 577
Server App | MSTR_SURVEY_TRXN_TBL
MSTR_SURVEY_TBL
MSTR_CORP_SURVEY_MPNG_TBL
MSTR_CORPORATE_SURVEY_GROUPS_TBL

## Lead(I-Refer)
Poject Name | Issue Name | MileStone | Status | Description
Server App | iRefer-Phase-2-Lead-MyLead | mil-2024-OCT-iRefer-Phase-2-Lead | Live | Integrating New Lead vendor (from S-CRM to I-CRM)
Server App | iRefer-Phase-2-Lead-MyLead | mil-2024-OCT-iRefer-Phase-2-Lead | Live | Integrationg My Lead API from New Vendor
Server App | I-Refere-Phase3-MyLead_Detail | mil-2025-MAR-IRefer-Lead-Project-Phase-3 | Live | Introducing Lead detail Page whcih is taken from e_ngage DB
Server App | I-Refer-Phase-3-DB-Patch | mil-2025-JAN-Database-Fixes-Patch | Live | Phase 3 DB patch
Server App | I-refer-Phase-4-DB-Patch | mil-2025-JAN-Database-Fixes-Patch | Live | DB pathc for Admin Product List Admin Manager
Server IB | iRefer-Phase-2-Lead | mil-2024-OCT-iRefer-Phase-2-Lead | Live | Integrating New Lead vendor (from S-CRM to I-CRM)
Server IB | IssueiRefer-Phase-2-Lead-MyLead | mil-2024-OCT-iRefer-Phase-2-Lead | Live | Integrationg My Lead API from New Vendor
Server IB | I-refere-live-Credentials | mil-2024-OCT-iRefer-Phase-2-Lead | Live | Changing credentials from UAT to PROD before going to production
Server IB | I-refer-phase-2-prod-bug-fix | mil-2024-OCT-iRefer-Phase-2-Lead | Live | There was a issue in the url from the third party
Server IB | I-Refer-Lead-DNS-Change | mil-2025-NOV-iRefer-Lead-API-Domain-Changes | Live | The third chnaged their Domain Name
Server Admin | I-Refer-Phase-4-Product-List-Menu | mil-2025-JUL-irefer-Phase-4 | Live | Admin Menu to Manage the products for lead creation

## UAN Linking
Poject Name | Issue Name | MileStone | Status | Description
Server App | UAN Linking issue | mil-2024-DEC-Form-11-UAN-Linking-In-UOTM | Live | Correcting the aadhar and pan and ifsc no mismatch and removing aadhar from auditing
Server App | UAN-Linking-DB-Patch | mil-2025-JAN-Database-Fixes-Patch | Live | HR4U and e_ngage procedures to store and retrive data
Server IB | UAN Linking Live Issue | mil-2024-DEC-Form-11-UAN-Linking-In-UOTM | Live | Integrating UIDAI reference number API.

## HummingBird Gateway
Poject Name | Issue Name | MileStone | Status | Description
Server App | Humming-Bird-Gateway-Implementation | mil-2025-APR-Hummingbird-API-Integration | Live | Integrating API Gateway for humming bird api. First the third praty api was called directly now it is called trhough API Gateway
Server IB | HummingBird-GateWay-Implementation | mil-2025-APR-Hummingbird-API-Integration | Live | Integrating API Gateway for humming bird api. First the third praty api was called directly now it is called trhough API Gateway
Server IB | Humsafar-HummingBird-API-DNS-Change | mil-2025-NOV-Humsafar-Hummingbird-API-Domain-Changes | Live | The third party changed their domain name.

## Issues and Bug Fixes
Poject Name | Issue Name | MileStone | Status | Description
Server App | UOTM Muster issue | mil-2024-OCT-Database-Fixes-Patch | Live | Some users were unable to apply muster , it was due to trc codes issue in Fusion_Get_EmplMusterCode, it is not used now as fusion is not used and peoplesoft is used.
Server App | More-than-2-User-Iive-Issue | mil-2025-JAN-Database-Fixes-Patch | Live | There were more than 2 entries for some user in MSTR_USER_LOGIN_TBL , sue to which some users were unable to login and register. So this was to delete those and adding unique constraint to (LOGIN_ID) column
Server App | More-Than-2-User-live-Issue-Phase-2 | mil-2025-JAN-Database-Fixes-Patch | Live | Some entries were still left , edge cases remained this patch was to tackle them
Server App | Hide-Qr-Code | mil-2025-JAN-Database-Fixes-Patch | Live | This patch was to hide the QR-code menu, becasue it was decommisioned.
Server App | Get_Event_Data_Patch | mil-2025-JAN-Database-Fixes-Patch | Live | Fixed the select queries in this procedure , this was to fix login time issue
Server App | Fusion-Muster-Reasons-Update-DB-Patch | mil-2025-JAN-Database-Fixes-Patch | Live | Updating Muster Reasons , becasue some error was encountered because of this
Server App | GeoTag-Duplicate-Data-Removal-DB-Patch | mil-2025-JAN-Database-Fixes-Patch | Live | Removing duplicate location data
Server App | Cookie-Misconfiguration | mil-2025-SEP-Cookies-Misconfiguration | Live | This was to resolve a vulnerabilty, cookie mi-sconfiguration , cookies were not properly set
Server App | App-Drawer-Visibility-Fix | mil-2025-JAN-Database-Fixes-Patch | Live | App Drawer was not visible to some users
Server App

## Karix(Mobile Binding)
Poject Name | Issue Name | MileStone | Status | Description
Server App | Register-By-Pass-Fix-With-Time-Based-Session | mil-2026-JAN-Login-Bypass-Fix | Live | Fixing the vulnerability, of login by-passs
Server App | Karix-Vul-Fix-DB | mil-2025-JAN-Database-Fixes-Patch | Live | DB patch of Login by-pass Vulnerability

## Sheet10
Poject Name | Issue Name | MileStone | Status | Description